## Sheet1
Not Started
In Progress
Completed
Sprint 1 Backlog : Task Description | Duration (Time in Hours) | Who | Status | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
Portfolio Worth
Background Research Into Stock Market | 16 |  | Not Started
Background Research Into Android | 4 |  | Not Started
Find reliable datasource that can be used with the application | 2 |  | Not Started
Design Database | 1 |  | Not Started
Build Database to store stock market data | 2 |  | Not Started
Test database | 1 |  | Not Started
Design interface for application | 1 |  | Not Started
Implement interface for application | 4 |  | Not Started
Test interface | 3 |  | Not Started
Integrate Database and interface | 4 |  | Not Started
Test integration of database and interface | 3 |  | Not Started
Sprint 1 Total Hours Remaining | 41