## Sprint1Backlog
Not Started
In Progress
Completed
Sprint 1 Backlog : Task Description | Duration (Time in Hours) | Who | Status | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
Portfolio Worth
Background Research Into Stock Market | 4 | Goodman | Completed | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Background Research Into Android Platform | 16 | Gorman | Completed | 16 | 12 | 10 | 8 | 6 | 4 | 2 | 1 | 0 | 0
Find reliable datasource that can be used with our application | 2 | Andrew | Completed | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Implement code for gathering stock market data | 2 | Goodman | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Test stock data gathering code | 1 | Goodman | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Design Database | 1 | Goodman | Completed | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Build Database to store stock market data | 2 | Petko | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Test database | 1 |  | Not Started | [10 empty] | ???
Design interface for viewing total portfolio value | 1 | Gorman | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Implement interface for viewing total portfolio value | 4 | Petko | Completed | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0
Test interface | 3 | Petko | In Progress | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1
Integrate Database and interface | 4 |  | Not Started | [10 empty] | ???
Test integration of database and interface | 3 |  | Not Started | [10 empty] | ???
Create Sprint Backlog and task responsibilities | 2 | Andrew | Completed | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Download and install Eclipse, Android SDK, plugins and components | 8 | Andrew | Completed | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Configure Android platform | 2 | Andrew | Completed | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design Black Box Tests and get approval from JASS | 1 | Goodman | In Progress | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Design Acceptance Tests and get approval from JASS | 1 | Goodman | In Progress | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Perform Daily Scrums | 2 | Petko | In Progress | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
Plan Sprint Review | 1 | Petko | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Plan Sprint Retrospective | 1 | Goodman | Completed | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Perform Sprint Retrospective | 1 | Goodman | Not Started | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Perform Sprint Review | 1 | Petko | Not Started | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Sprint 1 Total Hours Remaining | 64 |  |  | 56 | 50 | 44 | 34 | 29 | 24 | 17 | 11 | 7 | 7

## Sprint2Backlog
Not Started
In Progress
Completed
Sprint 2 Backlog : Task Description | Duration (Time in Hours) | Who | Status | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
Refactor Sprint 1 | 4 | Goodman | In Progress
Design new Interface mockups | 3 | Gorman | In Progress
Display time of last update | 1 | Goodman | Not Started
Update portfolio to include Bowleven Share set | 1 | Petko | Completed
Price Fall
Add Feature to check for Internet Connection Status | 4 | Petko | In Progress
Gather Market Open Values | 1 | Andrew | In Progress
Compare stock value from market open to current time | 2 | Andrew | Not Started
Implement status page | 4 | Gorman | In Progress
Test integration of Price Fall with Portfolio Worth | 2 | Andrew | In Progress
Design Acceptance/Unit Tests and get approval from JASS | 2 | Goodman | In Progress
Price Rise
Compare stock value from market open to current time | 2 | Andrew | Not Started
Test integration of Price Rise with Price Fall and Portfolio Worth | 2 | Andrew | Not Started
Create Sprint Backlog and task responsibilities | 2 | Andrew | In Progress
Perform Daily Scrums | 4 | Petko | In Progress
Plan Sprint Review | 1 | Gorman | Not Started
Plan Sprint Retrospective | 1 | Petko | Not Started
Perform Sprint Review | 1 | Gorman | Not Started
Perform Sprint Retrospective | 1 | Petko | Not Started
Sprint 2 Total Hours Remaining | 38